MPC BSI PROPOSAL

UNIVERSAL LEARNING DESIGN & SMARTXT

Submitted by Terria Odom-Wolfer / Kathleen Rozman 4/14/2009

The Smartxt project at MPC began in the spring of 2009 and represents a collaborative effort between Supportive Services & Instruction, TRIO/SSS, English & Study Skills Center, and several instructors in the English Department.  Smartxt projects, which integrate Kurzweil technology into mainstream classes, are emerging across the state in community colleges, and are being adapted to suit the needs of individual students. The goal of the project is to adapt this technology into mainstream courses so its use could benefit all students, including those with undiagnosed learning challenges, basic skills needs or ESL, thereby embracing the spirit of universal design and facilitating learning for all students. This project involves students using technology to advance their basic skills needs, and it incorporates the effective use of the software by integrating it into the regular course curriculum. The technology is available for students to utilize in several areas of campus—the ESSC, the TRIO/SSI Lab, and both of the Supportive Services & Instruction labs.

In the first phase of the project we identified the interested parties and developed the plan for implementation at MPC. The Kurzweil software has been purchased and the alternate media specialist has worked with the faculty on digitizing the material used for the March training and the spring projects.  On March 20th, 2009 a staff training was held at the college.  Twenty-nine people including faculty, staff, administrators, potential student mentors and off-campus faculty (Foothill College, Hartnell, and CSUMB) participated. Participants were introduced to a broad range of reading, writing, and study skills built into the Kurzweil 3000 software.  In addition, the Smartxt concept was introduced and strategies for embedding textbooks to guide students’ learning and engage them in the reading process and in utilizing their textbooks effectively were presented.  In the afternoon, faculty worked on practicing the text embedding and engaging in discussion of how this technology could be implemented to help students in multiple disciplines.  In mid April two English faculty will introduce the Smartxt concept to their English 321 classes.  In Fall 2009, an additional English instructor will utilize the Kurzweil Smartxt instructional model in two sections of her English 301 class.

We are now planning the second phase of the project.  The project team is working on implementing the instructional plan while at the same time, exploring additional collaborations in order to expand the involved instructional areas and locations.  We are planning additional trainings for both experienced and novice faculty and staff, and we will be initiating the process for obtaining publisher permissions for digitizing texts.  We also hope to visit some campuses who are involved in the Kurzweil Smartxt project in order to network and observe how others are implementing the program.  Another goal for the next year is to investigate the use of student mentors to train and work with other students.  A critical factor for the project’s success involves the identification of a location on campus that can be designated for staff and student training as well as support from the college technology administrator.  Staff will be needed to assist in networking and installing software in various locations where it will be used on campus.  Without these important components in place, it will be extremely difficult for the project to move forward in the coming year.

BSI FUNDING REQUEST FORM:	SECTION I						FISCAL YEAR: 		2009-10

All completed funding request forms must be submitted to BSI Committee Chairperson no later than 5:00pm on April 14, 2009.

| Priority Number (Only for Budget- Dependent Items) | Dept./Area | Description (Please briefly describe the proposed activity/item) | Meets BSI Long-Term Goal(s) (A, B, C, D) | Meets BSI Expenditure Item(s) and Corresponding Effective Practice(s) (Specify Items/Practices) | Total Cost | Ongoing (OG) or One-Time (OT) Expense |
| --- | --- | --- | --- | --- | --- | --- |
|  | Supportive Services, TRIO, ESSC, English Dept. Reading Center | Universal Learning Design Smart Txt Project | A B D | Category F #1: Instructional Materials A.1.4: Developmental education is adequately funded/staffed A.5.1: Course related learning assistance Category D #3: Supplemental Instruction/Tutoring D.10.6: Tutors receive formal training in subject matter/effective pedagogy for the discipline Category G #1: Other Purposes C.1.2: Professional development activities for developmental education are actively supported by senior administration | $27,850 | (OT) |

Please list the collaborative partners of your project(s):

Supportive Services, TRIO/SSS, ESSC, English Dept., Reading Center

BSI FUNDING REQUEST FORM:	SECTION II					FISCAL YEAR: 		2009-10

All completed funding request forms must be submitted to the BSI Committee Chairperson no later than 5:00pm on April 14, 2009.

| Activity/Item | Budget Detail | Rationale | Anticipated Outcomes and Method of Evaluation | Responsible Individual(s) | Timeframe for Implementation |
| --- | --- | --- | --- | --- | --- |
| Continuation of work with experienced faculty and identification of additional faculty to participate in training and implementation of Kurzweil Smartxt | $2,500 | Experienced faculty will need to be compensated for their time/work as they continue to implement Kurzweil New faculty/staff will be identified and trained in use of Kurzweil software | Staff will demonstrate ability to utilize Kurzweil Faculty will use Kurzweil to enhance their instruction and help strengthen students’ metacognitive skills Students will initiate and create innovative ways to expand their Kurzweil use | Terria Odom-Wolfer Kathleen Rozman | Fall ’09-Spring ‘10 |
| Campus Coordination | $9,000 | Continued coordination, training, project management, troubleshooting and various other duties need to be completed to assure that the project continues in an organized and professional manner | The project will continue with experienced faculty as well as expand to include new collaborations and reach more students | Terria Odom-Wolfer Kathleen Rozman | Fall ’09-Spring ‘10 |
| Equipment | $1,000 | Equipment is needed to digitize and store and disseminate text | Text will be digitized, organized and disseminated with efficiency and quality | Terria Odom-Wolfer Kathleen Rozman Alexis Copeland | Fall ’09-Spring ‘10 |
| College infrastructure | $6,600 | Purchasing, trouble-shooting and upgrades of campus software Work with college technology staff to network and install upgrades Conference with on- and off-campus consultants | Publisher permission granted Software upgrade and purchase | Alexis Copeland Kathleen Rozman | Fall ’09-Spring ‘10 |
| Alternate Media Production | $3,000 | Instructional materials need to be digitized and edited to ensure and promote access and ease of use Faculty need to consult with Alternate Media specialist regarding publisher permissions and various technical issues | Faculty will have access to digitized instructional materials to use for embedding Students will be able to access faculty embedded instructional materials once they have shown documentation that they have purchased the text | Alexis Copeland and staff | Fall ’09-Spring ‘10 |
| Training | $2,500 | Advanced training needs to be provided for experienced faculty to learn more tools and application of software New faculty and staff will need to be trained in the use of Kurzweil software and the implementation of the instructional delivery model | Staff will demonstrate ability to utilize Kurzweil Faculty will use Kurzweil to help strengthen students’ metacognitive skills | Terria Odom-Wolfer Kathleen Rozman | Fall ’09- Spring ‘10 |
| Training/Collaboration with other colleges using Kurzweil Smartxt model | $1,000 | Networking with other colleges will enhance our ability to be more effective | Coordinators will gather and disseminate information from other sites involved in project | Terria Odom-Wolfer Kathleen Rozman | Fall ’09- Spring ‘10 |
| Identification of space on campus | n/a | In order for the project to be successful, a designated space on campus must be identified for student/staff training | A designated space on campus will be identified for use in project | Terria Odom-Wolfer Kathleen Rozman Academic Affairs Adminstration | Fall ’09 |
| Student Mentor identification and training | $1,250 | Students are more engaged and learn to use the tools more effectively when they are teaching others how to use the software Students feel comfortable learning new skills and asking questions in a peer group Faculty will have more time to create study strategies and embed text | A student support system/learning community will be developed around the implementation and use of the Kurzweil Smartxt Student mentors will be compensated for their time and training to assist in reinforcing the importance of their roles in the project | Terria Odom-Wolfer Kathleen Rozman | Fall ’09- Spring ‘10 |
| Miscellaneous/ Unanticipated Expenses | $1,000 | During the first semester of the project, unanticipated costs and expenses emerged. This expenditure item will allow for flexibility in the budget to deal with unanticipated expenses when they arise. | Unexpected expenses/items can be dealt with in a timely manner | Terria Odom-Wolfer Kathleen Rozman |  |

Total Costs = $27,850